## Sheet1
is the project over budget? | yes by 1500 hrs | Time(days) | Earned value | Actual cost
is the project delayed? | it depends on the estimated avg working hours and the actual working hours | 0 | 0 | 0
| assuming that they are the same and equal 10 hrs/day for each engineer | 35 | 1375 | 1750
| then the project is delayed by (140-110) 30 days | 70 | 2750 | 3500
| actual number of days now is 140 days | 105 | 4125 | 5250
|  | 140 | 5500 | 7000